Excel Automation

Video Production Guide  v3

Updated March 2026 — Reflects new features, restructured Video 3

| FIELD | DETAIL |
| --- | --- |
| Project | 3 Training Videos for SharePoint — Excel Automation Toolkit |
| Narrator | ElevenLabs Built-In Voice ¦ ID: GzE4TcXfh9rYCU9gVgPp |
| Total Clips | 39 clips across 3 videos ¦ Script version: v3 |
| Actions | 65 Command Center actions (was 62) |
| Universal Tools | 140+ tools across 23 VBA modules + 22 Python scripts (was ~100) |
| Recording Tool | Camtasia (free 30-day trial — record AND edit in one tool) |
| Audio Generation | ElevenLabs API via Google Colab on work laptop |
| Cost | ElevenLabs ~$5-11 one month ¦ Everything else free |
| Status | Audio needs full regeneration (v3 script ready). Next: Record in Camtasia. |

🆕 NEW: Script v3 includes: Splash Screen, What-If Scenario (Actions 63-65), Exec Brief, Time Saved Calculator, full Video 3 restructure with 23 modules

⚠ WATCH: All 39 clips need to be regenerated — too many scripts changed in v3 to reuse old audio. Delete ElevenLabs_Clips folder in Colab and run generate_clips_v3.py fresh.

SECTION 1 — Final Toolchain

| TOOL | PURPOSE & NOTES |
| --- | --- |
| ElevenLabs API | AI voice. Built-in voice ID: GzE4TcXfh9rYCU9gVgPp. Starter ~$5-11/mo. Cancel after clips generated. |
| Google Colab | Runs Python generation script in-browser. Works on work laptop — API calls not blocked. |
| Camtasia | Record AND edit in one tool. Free 30-day trial. Multi-track timeline — audio clip on track 1, screen recording on track 2. No second tool needed. |
| Box | File storage for scripts and guides. |

📌 NOTE: Descript and OBS are no longer part of the workflow. Camtasia replaces both. Snagit is also not needed — Camtasia has its own recorder.

SECTION 2 — Video Overview (v3 Changes Highlighted)

Video 1 — What's Possible (7 clips, ~5 min)

| Changes | Numbers only — 62→65 actions, ~100→140+ tools in V1_S6 and V1_S7 |
| --- | --- |
| New Stat Line | '65 actions. 140+ universal tools. Zero cost. Ten minutes vs ten hours.' |
| Clips to Regenerate | V1_S1, V1_S6, V1_S7 — all other clips unchanged in substance |

Video 2 — Full Demo Walkthrough (19 clips, ~18 min)

| New — V2_S0 | Opening now includes splash screen mention + existing disclaimer |
| --- | --- |
| New — V2_S10b | Executive Brief: one-click color-coded workbook status report (new clip) |
| New — V2_S13 | What-If Scenario Demo: Actions 63-65. Revenue/cost presets + Restore. TIER 1 WOW MOMENT (replaces Scenarios/Sensitivity) |
| New — V2_S13b | Time Saved Calculator: scans 65 actions, builds time savings report. CLOSING MOMENT (new clip) |
| Chapter 5 Structure | Executive Mode → Version Control → What-If → Integration Test → Audit Log → Time Saved |
| Clips Removed | Old V2_S13_Scenarios_Sensitivity replaced by What-If |
| Closing Stat | '65 actions. 140+ universal tools. Zero cost. Ten minutes vs ten hours.' |

Video 3 — Universal Tools (13 clips, ~10 min) — FULLY REBUILT

| Old Structure | Generic VBA clips covering individual tools one by one |
| --- | --- |
| New Structure | 4 chapters covering all 23 modules with 140+ tools |
| Chapter 1 | Data Cleanup: DataSanitizer, Highlights, Comments |
| Chapter 2 | Sheet & Column Tools: TabOrganizer, ColumnOps, SheetTools |
| Chapter 3 | Analysis & Building: Compare, Consolidate, PivotTools, LookupBuilder, ValidationBuilder |
| Chapter 4 | Universal Command Center — capstone demo of the full menu |
| Python | 2 Python clips retained (File Compare, PDF Extractor) — Fuzzy Lookup removed for time |
| Closing | Updated numbers — 140+ tools, 23 modules |

SECTION 3 — Universal Toolkit Reference (23 Modules)

Reference for what's in the toolkit. Use this when demoing Video 3 so you know exactly what each module contains.

| MODULE | TOOLS / WHAT IT DOES |
| --- | --- |
| modUTL_Core (9) | Shared utilities — StyleHeader, TurboOn/Off, logging backbone |
| modUTL_Audit (~10) | External links, hidden sheets, error scan — workbook health report |
| modUTL_Branding (2) | iPipeline brand colors and theme — one-click branded formatting |
| modUTL_DataQuality (~8) | Data scans, letter grade — same engine as Video 2 demo |
| modUTL_DataSanitizer (4) | Fix text-numbers, floating-point errors, blank rows, spaces |
| modUTL_Export (~5) | PDF and CSV export with headers/footers |
| modUTL_Formatting (~10) | AutoFit, borders, number formats, column widths |
| modUTL_Navigation (~5) | Table of contents, sheet index, hyperlinks |
| modUTL_Search (~3) | Cross-sheet keyword search |
| modUTL_SheetTools (3) | Sheet index, template cloner, customer IDs |
| modUTL_Utilities (~12) | General-purpose tools |
| modUTL_ProgressBar (1) | ASCII progress bar on status bar |
| modUTL_SplashScreen (1) | Standalone branded splash screen |
| modUTL_ExecBrief (1) | Universal workbook executive brief — color-coded status |
| modUTL_ColumnOps (7) | Column insert/delete/move/split/merge/fill/swap |
| modUTL_Compare (1) | Sheet comparison with color-coded diff report |
| modUTL_Consolidate (1) | Multi-sheet consolidation with source tracking |
| modUTL_Highlights (3) | Threshold, top/bottom N, duplicate detection |
| modUTL_PivotTools (4) | PivotTable create/refresh/style/drill |
| modUTL_TabOrganizer (6) | Sort/color/group/reorder/rename tabs in bulk |
| modUTL_Comments (3) | Extract/clear/convert comments and notes |
| modUTL_ValidationBuilder (5) | Data validation builder — no formula writing needed |
| modUTL_LookupBuilder (2) | VLOOKUP/INDEX-MATCH formula builder |
| modUTL_WhatIf (1) | Universal What-If scenarios — also in main file as Actions 63-65 |
| modUTL_CommandCenter (1) | Master menu for all 140+ tools — 13 categories, keyword search |

SECTION 4 — Audio Generation (v3 — Regenerate All)

⚠ WATCH: All 39 clips need regeneration. Too many scripts changed to reuse v2 audio. Delete ElevenLabs_Clips folder in Colab first.

| 1 | Open Google Colab colab.research.google.com — works on work laptop, API not blocked |
| --- | --- |

| 2 | Install ElevenLabs Cell 1: !pip install elevenlabs → run |
| --- | --- |

| 3 | Clear old clips Cell 2: !rm -rf ElevenLabs_Clips → run |
| --- | --- |

| 4 | Run generate_clips_v3.py Paste full script into Cell 3. Add API key on line 24. Run. Watch 39/39 counter. |
| --- | --- |

| 5 | Download Terminal → zip -r clips.zip ElevenLabs_Clips/ → Files panel → right-click → Download |
| --- | --- |

SECTION 5 — Screen Recording in Camtasia

Pre-Recording Setup

| - Close all apps except Excel - Notifications off (Focus Assist → Do Not Disturb) - Clean desktop — no icons visible - Screen resolution: 1920x1080 - Excel open on correct file and correct starting sheet - Command Center closed, output sheets deleted | - Headphones in — audio clips folder open - Recording Cue Sheet v3 open on phone or second monitor - Set Camtasia hotkey to start/stop recording - For Video 3: messy sample file open — NOT the P&L file - For Video 3 Python clips: sample files prepared and easy to find - For Video 2: GL source CSV saved somewhere easy to find |
| --- | --- |

Key Moments to Nail in Video 2

| MOMENT | WHAT TO DO |
| --- | --- |
| Splash screen (V2_S0) | Hold on splash screen 2-3 full seconds before it dismisses |
| Variance Commentary (V2_S6) | HOLD STILL at 0:10 and 0:32 — do not scroll during silence |
| What-If Demo (V2_S13) | Hold on Assumptions sheet BEFORE and AFTER restore — 3 sec each |
| Exec Brief (V2_S10b) | Hold on color-coded status 3 sec before scrolling |
| Time Saved (V2_S13b) | Hold on annual savings number — last thing viewers see before close |

SECTION 6 — Editing in Camtasia

| 1 | New project File → New Project. Canvas: 1920x1080. |
| --- | --- |

| 2 | Import all files for Video 1 Import MP3 clips and MP4 screen recordings into Media Bin. |
| --- | --- |

| 3 | Audio backbone first Drag MP3s to Track 1 in order. 0.5-1 sec gap between each clip. |
| --- | --- |

| 4 | Title card at start Add opening title card PNG. 3 second hold. Fade into first recording. |
| --- | --- |

| 5 | Disclaimer card for Video 2 Add V2_Disclaimer_Title_Card.png before V2_S0 audio starts. 3-4 seconds. |
| --- | --- |

| 6 | Lay in screen recordings Drag MP4s to Track 2. Drag left/right to sync with narration. |
| --- | --- |

| 7 | Trim Trim start and end of each video clip so only relevant action shows. |
| --- | --- |

| 8 | Review and export Full playback check. Share → Export → Local File → MP4 → 1920x1080 High Quality. |
| --- | --- |

💡 TIP: Build and export Video 1 completely before starting Video 2. It's the shortest and confirms your workflow.

SECTION 7 — Title Cards (All Built, Ready to Use)

| FILE | USE |
| --- | --- |
| V1_Title_Card.png | Opening card — Video 1 'What's Possible' ¦ Hold 3 sec |
| V2_Title_Card.png | Opening card — Video 2 'Full Demo Walkthrough' ¦ Hold 3 sec |
| V2_Disclaimer_Title_Card.png | Disclaimer card — Video 2 only, before V2_S0 audio ¦ Hold 4 sec |
| V3_Title_Card.png | Opening card — Video 3 'Universal Tools' ¦ Hold 3 sec |

SECTION 8 — Master Checklist v3

Audio

| - ✅ Voice selected (ID: GzE4TcXfh9rYCU9gVgPp) - ✅ generate_clips_v3.py ready (in Box + downloaded) - ⬜ Regenerate all 39 clips in Colab (delete old folder first) | - ⬜ Download and organize clips into Video1/Video2/Video3 - ⬜ Rotate ElevenLabs API key (exposed in chat — do this after recording) |
| --- | --- |

Pre-Recording Prep

| - ⬜ Prepare GL source CSV for Video 2 GL Import demo - ⬜ Prepare two Excel versions for Video 3 file comparison - ⬜ Prepare fuzzy lookup sample file for Video 3 - ⬜ Prepare PDF with table for Video 3 PDF Extractor - ⬜ Prepare messy sample spreadsheet for Video 3 | - ⬜ Confirm splash screen fires on file open (Video 2) - ⬜ Confirm What-If presets work — all 7 plus Restore - ⬜ Confirm Time Saved Calculator generates report - ⬜ Confirm Exec Brief generates color-coded brief |
| --- | --- |

Recording

| - ⬜ Test run: record V1_S1 only (25 seconds) - ⬜ Record all 7 Video 1 segments | - ⬜ Record all 19 Video 2 segments - ⬜ Record all 13 Video 3 segments |
| --- | --- |

Editing & Delivery

| - ⬜ Build and export Video 1 in Camtasia - ⬜ Build and export Video 2 in Camtasia - ⬜ Build and export Video 3 in Camtasia | - ⬜ Upload all 3 MP4s to SharePoint - ⬜ Upload guides and script to SharePoint |
| --- | --- |

SECTION 9 — Supporting Files

| FILE | DESCRIPTION |
| --- | --- |
| generate_clips_v3.py | Current production script. All 39 clips, v3 scripts. Add API key on line 24. |
| Recording_Cue_Sheet_v3.docx | Timestamp-by-timestamp cue sheet for all 39 clips. Keep open while recording. |
| Video_Production_Guide_v3.docx | This document. |
| V1_Title_Card.png | Opening title card for Video 1. |
| V2_Title_Card.png | Opening title card for Video 2. |
| V2_Disclaimer_Title_Card.png | Fictional data disclaimer card for Video 2. |
| V3_Title_Card.png | Opening title card for Video 3. |

Excel Automation Video Project v3 | Connor Atlee | March 2026